## Project Schedule
ID | Level | Name | Duration (days) | Start | Finish | Predecessors | Resource Names | Notes
1 | 0 | FA26SE238 - DroneOps Intelligence | 75 | 2026-09-07 08:00 | 2026-12-18 17:00 |  | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | 15 semester weeks; provisional dates assume W1 starts 07 Sep 2026. Four members / four main flows. Actual review and council appointments: TBA.
2 | 0 | Stage 1 - Initiation, Feasibility & Scope | 30 | 2026-09-07 08:00 | 2026-10-16 17:00 |  | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Official phase W1-W6; design prototypes may overlap after Review 1.
3 | 1 | Project Registration / Supervisor Coordination | 4 | 2026-09-07 08:00 | 2026-09-10 17:00 |  | ThongLQ | Confirm registration form, group, supervisors and reviewers; carry forward any work completed before semester.
4 | 1 | Prepare Report 1 - Project Introduction | 4 | 2026-09-07 08:00 | 2026-09-10 17:00 |  | ThongLQ | Scope, actors, context and ten features; four main flows and external AI API.
5 | 1 | Submit Report 1 | 0 | 2026-09-11 17:00 | 2026-09-11 17:00 | 4 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | End W1 deadline; supervisor review.
6 | 1 | Prepare Report 2, WBS, Schedule & Risk Plan | 4 | 2026-09-14 08:00 | 2026-09-17 17:00 | 5 | NghiaHQ; KhanhGNG; ThongLQ | Four-flow owners, provisional effort and weekly capacity; align with official review gates.
7 | 1 | Submit Report 2 + Project Schedule | 0 | 2026-09-18 17:00 | 2026-09-18 17:00 | 6 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | End W2 deadline.
8 | 1 | Technical Feasibility Prototypes | 10 | 2026-09-14 08:00 | 2026-09-25 17:00 |  | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Prototype tasks share member availability; durations are elapsed windows.
9 | 2 | MAVLink / MQTT / WebSocket Prototype | 8 | 2026-09-14 08:00 | 2026-09-23 17:00 |  | KhanhGNG | Simulator ingestion, normalization and persistence. ¦ Responsible: KhanhGNG. Team support as needed.
10 | 2 | Map / Geofence Prototype | 8 | 2026-09-14 08:00 | 2026-09-23 17:00 |  | NghiaHQ | Route, restricted areas and altitude validation. ¦ Responsible: NghiaHQ. Team support as needed.
11 | 2 | OpenAI or Gemini API Prototype | 8 | 2026-09-14 08:00 | 2026-09-23 17:00 |  | ThongLQ | Mission context, response display, server-side keys, timeout/rate limits; no model training. ¦ Responsible: ThongLQ. Team support as needed.
12 | 1 | Report 3 Overview, Actors, Use Cases & Project Tracking | 4 | 2026-09-21 08:00 | 2026-09-24 17:00 | 7 | NghiaHQ | Product Overview, User Requirements, System Functional Overview; each flow owner contributes.
13 | 1 | Prepare Review 1 Slides, Registration & Document Package | 3 | 2026-09-23 08:00 | 2026-09-25 17:00 | 12SS+2 days | ThongLQ; NghiaHQ | Registration, Reports 1-2, Report 3 overview, context/actors/use cases and Project Tracking.
14 | 1 | Submit Review 1 Dossier | 0 | 2026-09-25 17:00 | 2026-09-25 17:00 | 12;13 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Common deadline END W3 regardless of appointment in W4 or W5; also satisfy at least 2 working days before actual review.
15 | 1 | Review 1 - Feasibility & Requirements (provisional W4) | 0 | 2026-10-02 17:00 | 2026-10-02 17:00 | 14 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Official window W4-W5; group date TBA. Record and circulate agreed minutes before session closes; allow 48 calendar hours for supplementary feedback.
16 | 1 | Resolve Review 1 Feedback / Update Registration | 9 | 2026-10-05 08:00 | 2026-10-15 17:00 | 15 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | If actual review is W5, adjust this window; revise scope where required and obtain supervisor confirmation.
17 | 1 | Freeze Registration / Scope | 0 | 2026-10-16 17:00 | 2026-10-16 17:00 | 16 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Mandatory END W6: confirmed registration is the scope baseline for Review 2 and Council 1.1.
18 | 0 | Stage 2 - Requirements, Design & Package 1 | 25 | 2026-10-05 08:00 | 2026-11-06 17:00 |  | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Preparatory work W5-W6; official design phase W7-W9. Package 1 must be ready by end W7.
19 | 1 | Complete SRS: Screens, Authorization, Rules & Interfaces | 10 | 2026-10-05 08:00 | 2026-10-16 17:00 | 15 | NghiaHQ | Include mockups, state rules, normal/exception flows, draft ERD and measurable NFRs; no invented thresholds.
20 | 1 | Architecture, Database & Integration Contracts | 10 | 2026-10-05 08:00 | 2026-10-16 17:00 | 15 | NghiaHQ; ThongLQ | System/database/package design; account/UAV/operator data, telemetry, incidents and external AI API. ¦ Responsible: NghiaHQ; ThongLQ. Team support as needed. Existing stack: Next.js (ThongLQ), C# / ASP.NET Core (NghiaHQ), Supabase PostgreSQL (ThongLQ).
21 | 1 | MF1 Detailed Design - Planning & Pre-flight Validation | 7 | 2026-10-07 08:00 | 2026-10-15 17:00 | 20SS+2 days | NghiaHQ | FE-02/03/04; route validation, edit permissions, approval/rejection and state diagrams. ¦ Responsible: NghiaHQ. Team support as needed.
22 | 1 | MF2 Detailed Design - Monitoring & Incident Management | 8 | 2026-10-12 08:00 | 2026-10-21 17:00 | 20SS+5 days | KhanhGNG | FE-05/06/07/08/10; telemetry, connectivity, detection, alerts and incident states. ¦ Responsible: KhanhGNG. Team support as needed.
23 | 1 | MF3 Detailed Design - Post-Flight & Mission History | 8 | 2026-10-12 08:00 | 2026-10-21 17:00 | 20SS+5 days | DucDDA | FE-08/10; mission completion, history, reports and analytics. ¦ Responsible: DucDDA. Team support as needed.
24 | 1 | MF4 Detailed Design - AI API Risk Assessment | 8 | 2026-10-12 08:00 | 2026-10-21 17:00 | 20SS+5 days | ThongLQ | FE-09/10; source mission context, external API contract, advisory UI and failure states. ¦ Responsible: ThongLQ. Team support as needed.
25 | 1 | Iteration 1 - MF1 + Shared FE-01 / Software Package 1 | 5 | 2026-10-19 08:00 | 2026-10-23 17:00 |  | NghiaHQ | MF1 lead NghiaHQ; implement agreed initial scope after W6 freeze. Reuse validated prototypes and peer support. ¦ Responsible: NghiaHQ. Team support as needed.
26 | 2 | Implement FE-01 UAV/Operator Management & Access | 4 | 2026-10-19 08:00 | 2026-10-22 17:00 | 17;20 | NghiaHQ; ThongLQ | Shared management, authentication/authorization foundation for four flows. ¦ Responsible: NghiaHQ; ThongLQ. Team support as needed.
27 | 2 | Implement Mission Planning, Waypoints & Validation | 4 | 2026-10-19 08:00 | 2026-10-22 17:00 | 17;21 | NghiaHQ | FE-02/04; reuse geospatial prototype; route and altitude checks. ¦ Responsible: NghiaHQ. Team support as needed.
28 | 2 | Implement Mission Approval Workflow | 3 | 2026-10-20 08:00 | 2026-10-22 17:00 | 27SS+1 day | NghiaHQ | FE-03; Operator submission, Operations Manager review/approve/reject. ¦ Responsible: NghiaHQ. Team support as needed.
29 | 2 | Test MF1 / Shared Functions and Assemble Package 1 | 3 | 2026-10-21 08:00 | 2026-10-23 17:00 | 26SS+2 days;27SS+2 days;28SS+1 day | NghiaHQ | Test delivered builds in parallel; final package requires shared/mission/approval work complete; source code and database scripts. ¦ Responsible: NghiaHQ. Team support as needed.
30 | 1 | Finalize Review 2 SRS, SDD, Test Plan & Slides | 5 | 2026-10-19 08:00 | 2026-10-23 17:00 | 19;20 | NghiaHQ; ThongLQ | Integrate remaining flow designs by Wed W7. Reports 3-4, Report 5 plan, updated Reports 1-2 and Tracking; system/database/package/state diagrams and workflow demo.
31 | 1 | Submit Review 2 Dossier + Software Package 1 | 0 | 2026-10-23 17:00 | 2026-10-23 17:00 | 29;26;27;28;30;22;23;24 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Mandatory END W7; SRS, SDD, Test Plan, code and database scripts; at least 2 working days before actual review.
32 | 1 | Review 2 - SRS, Design & Mandatory Features (provisional W8) | 0 | 2026-10-30 17:00 | 2026-10-30 17:00 | 31 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Official window W8-W9; group date TBA. Confirm required feature list within frozen scope; circulate agreed minutes at session end and allow 48-hour feedback.
33 | 1 | Resolve Review 2 Feedback / Baseline Mandatory Features | 5 | 2026-11-02 08:00 | 2026-11-06 17:00 | 32 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Update SRS/SDD/Test Plan and task backlog. If review is W9, record feature list immediately and carry non-blocking updates into W10.
34 | 0 | Stage 3 - Development & Testing | 20 | 2026-11-09 08:00 | 2026-12-04 17:00 |  | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Official W10-W13; Package 2 end W11, full product/tests/Report 6 draft end W13.
35 | 1 | Iteration 2 - MF2 / Software Package 2 | 10 | 2026-11-09 08:00 | 2026-11-20 17:00 | 33 | KhanhGNG | MF2 lead KhanhGNG; monitoring and incidents are one main flow. ¦ Responsible: KhanhGNG. Team support as needed.
36 | 2 | Implement MAVLink Gateway & Telemetry Persistence | 4 | 2026-11-09 08:00 | 2026-11-12 17:00 | 33 | KhanhGNG | FE-05; normalize, persist and update UAV/mission state. ¦ Responsible: KhanhGNG. Team support as needed.
37 | 2 | Implement Real-Time Monitoring Dashboard | 4 | 2026-11-10 08:00 | 2026-11-13 17:00 | 36SS+1 day | KhanhGNG | FE-06/10; location, altitude, speed, battery, connectivity and progress. ¦ Responsible: KhanhGNG. Team support as needed.
38 | 2 | Implement Incident Detection, Alerts & Management | 4 | 2026-11-16 08:00 | 2026-11-19 17:00 | 36;37 | KhanhGNG | FE-07/08; low battery, communication loss, abnormal altitude/speed, alerts and incident history. ¦ Responsible: KhanhGNG. Team support as needed.
39 | 2 | Test Complete MF2 / Update Reports 3-5 / Package 2 | 4 | 2026-11-17 08:00 | 2026-11-20 17:00 | 38SS+1 day | KhanhGNG | Incremental tests and demo; package source/database scripts and updated SRS, SDD and test records. ¦ Responsible: KhanhGNG. Team support as needed.
40 | 1 | Submit Software Package 2 + Updated Reports 3-5 | 0 | 2026-11-20 17:00 | 2026-11-20 17:00 | 39;38 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Mandatory END W11.
41 | 1 | Iteration 3 - MF3 + MF4 / Full Product | 10 | 2026-11-23 08:00 | 2026-12-04 17:00 |  | DucDDA; ThongLQ | MF3 lead DucDDA; MF4 lead ThongLQ. Parallel ownership with shared integration support. ¦ Responsible: DucDDA; ThongLQ. Team support as needed.
42 | 2 | Implement MF3 Post-Flight History, Reports & Analytics | 4 | 2026-11-23 08:00 | 2026-11-26 17:00 | 40 | DucDDA | FE-08/10; mission completion, flight history, telemetry, incidents, report and analytics. ¦ Responsible: DucDDA. Team support as needed.
43 | 2 | Implement MF4 External AI API Risk Assessment | 4 | 2026-11-23 08:00 | 2026-11-26 17:00 | 40 | ThongLQ | FE-09/10; prepare context, call configured OpenAI or Gemini API, validate/display advisory output and handle errors. ¦ Responsible: ThongLQ. Team support as needed.
44 | 2 | Integrate MF3/MF4 and Regress All Four Flows | 3 | 2026-11-25 08:00 | 2026-11-27 17:00 | 42SS+2 days;43SS+2 days | DucDDA; ThongLQ | Incremental tests; complete integration after implementation. Human review remains required for AI advice. ¦ Responsible: DucDDA; ThongLQ. Team support as needed.
45 | 1 | Feature-Complete Internal Build | 0 | 2026-11-27 17:00 | 2026-11-27 17:00 | 42;43;44 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Internal target before full system-test week; includes all ten features across four flows.
46 | 1 | System Testing / Defect Closure / Complete Report 5 | 4 | 2026-11-30 08:00 | 2026-12-03 17:00 | 45 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Four flows + shared functions, critical exceptions, test cases/results/defect list; release has no blocking Critical/Major defects.
47 | 1 | Performance, Telemetry & Geospatial Validation | 3 | 2026-11-30 08:00 | 2026-12-02 17:00 | 45 | KhanhGNG; NghiaHQ | Measure against baselined SRS thresholds; stability and connectivity scenarios. ¦ Responsible: KhanhGNG; NghiaHQ. Team support as needed.
48 | 1 | AI API Functional, Context & Failure-Handling Validation | 3 | 2026-11-30 08:00 | 2026-12-02 17:00 | 45 | ThongLQ | Mocked API cases plus controlled live smoke tests; missing context, invalid output, timeout/rate limits, latency and usage; user review of advice. ¦ Responsible: ThongLQ. Team support as needed.
49 | 1 | Draft Report 6 - Package, Installation & User Guides | 9 | 2026-11-23 08:00 | 2026-12-03 17:00 | 40 | ThongLQ; KhanhGNG | Draft during implementation; verify instructions against the integrated build by W13.
50 | 1 | Prepare Full Package, Reports 1-6 & Council 1.1 Demo | 4 | 2026-12-01 08:00 | 2026-12-04 17:00 | 46SS+1 day | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Registration frozen W6, Review 1/2 minutes, full source/database scripts, demo, tests, draft user guides and Project Tracking.
51 | 1 | Submit Council 1.1 Dossier | 0 | 2026-12-04 17:00 | 2026-12-04 17:00 | 46;47;48;49;50 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Mandatory END W13; all Report 1-6 materials and full package ready; at least 2 working days before actual session.
52 | 0 | Stage 4 - Council 1.1 / Council 1.2 | 10 | 2026-12-07 08:00 | 2026-12-18 17:00 |  | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Council 1.1 eligibility W14; Council 1.2 defense W15, conditional on passing 1.1.
53 | 1 | Council 1.1 Rehearsal & Document Consistency Check | 4 | 2026-12-07 08:00 | 2026-12-10 17:00 | 51 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Demonstrate mandatory feature list against registration/SRS/design; verify reproducible package and user guide.
54 | 1 | Council 1.1 - Defense Eligibility (provisional W14) | 0 | 2026-12-11 17:00 | 2026-12-11 17:00 | 51;53 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Official W14; actual date TBA. Three-member council. Pass -> Council 1.2; fail -> conditional Council 2.
55 | 1 | Prepare Report 7, Defense Slides & Final Package Draft | 4 | 2026-12-07 08:00 | 2026-12-10 17:00 | 51 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Prepare before Council 1.1 to meet the W15 submission lead time; include product, tests, Tracking and demo.
56 | 1 | Resolve Council 1.1 Feedback / Finalize Defense Package | 2 | 2026-12-14 08:00 | 2026-12-15 17:00 | 54;55 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Conditional on eligibility. Fix remaining findings, verify release and final Report 7, slides and database/source package.
57 | 1 | Submit Council 1.2 Dossier (provisional Tuesday W15) | 0 | 2026-12-15 17:00 | 2026-12-15 17:00 | 56 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | At least TWO WORKING DAYS before actual defense. Planned Tue 15 Dec 17:00 for Fri 18 Dec 17:00 defense; recalculate when actual appointment is announced.
58 | 1 | Defense Rehearsal / Final Environment Check | 2 | 2026-12-16 08:00 | 2026-12-17 17:00 | 57 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | All members practice demonstration and Q&A; preserve the submitted baseline.
59 | 1 | Council 1.2 - Official Defense (provisional W15) | 0 | 2026-12-18 17:00 | 2026-12-18 17:00 | 57;58 | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Official W15, conditional on passing Council 1.1; actual date TBA. Pass -> completion; fail -> Council 2 about four weeks later.
60 | 0 | Weekly Supervisor Meetings, Tracking & Weekly Reports | 75 | 2026-09-07 08:00 | 2026-12-18 17:00 |  | ThongLQ; NghiaHQ; KhanhGNG; DucDDA | Recurring each semester week: meet GVHD, update WBS/issues/defects/Q&A, submit Weekly Report, track risks/capacity and review feedback. 75 days is the recurrence window, not effort.

## Gantt
ID | Task | Start | Finish | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15
1 | FA26SE238 - DroneOps Intelligence | 2026-09-07 08:00 | 2026-12-18 17:00 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
2 | Stage 1 - Initiation, Feasibility & Scope | 2026-09-07 08:00 | 2026-10-16 17:00 | ■ | ■ | ■ | ■ | ■ | ■
3 | Project Registration / Supervisor Coordination | 2026-09-07 08:00 | 2026-09-10 17:00 | ■
4 | Prepare Report 1 - Project Introduction | 2026-09-07 08:00 | 2026-09-10 17:00 | ■
5 | Submit Report 1 | 2026-09-11 17:00 | 2026-09-11 17:00 | ◆
6 | Prepare Report 2, WBS, Schedule & Risk Plan | 2026-09-14 08:00 | 2026-09-17 17:00 |  | ■
7 | Submit Report 2 + Project Schedule | 2026-09-18 17:00 | 2026-09-18 17:00 |  | ◆
8 | Technical Feasibility Prototypes | 2026-09-14 08:00 | 2026-09-25 17:00 |  | ■ | ■
9 | MAVLink / MQTT / WebSocket Prototype | 2026-09-14 08:00 | 2026-09-23 17:00 |  | ■ | ■
10 | Map / Geofence Prototype | 2026-09-14 08:00 | 2026-09-23 17:00 |  | ■ | ■
11 | OpenAI or Gemini API Prototype | 2026-09-14 08:00 | 2026-09-23 17:00 |  | ■ | ■
12 | Report 3 Overview, Actors, Use Cases & Project Tracking | 2026-09-21 08:00 | 2026-09-24 17:00 |  |  | ■
13 | Prepare Review 1 Slides, Registration & Document Package | 2026-09-23 08:00 | 2026-09-25 17:00 |  |  | ■
14 | Submit Review 1 Dossier | 2026-09-25 17:00 | 2026-09-25 17:00 |  |  | ◆
15 | Review 1 - Feasibility & Requirements (provisional W4) | 2026-10-02 17:00 | 2026-10-02 17:00 |  |  |  | ◆
16 | Resolve Review 1 Feedback / Update Registration | 2026-10-05 08:00 | 2026-10-15 17:00 |  |  |  |  | ■ | ■
17 | Freeze Registration / Scope | 2026-10-16 17:00 | 2026-10-16 17:00 | [5 empty] | ◆
18 | Stage 2 - Requirements, Design & Package 1 | 2026-10-05 08:00 | 2026-11-06 17:00 |  |  |  |  | ■ | ■ | ■ | ■ | ■
19 | Complete SRS: Screens, Authorization, Rules & Interfaces | 2026-10-05 08:00 | 2026-10-16 17:00 |  |  |  |  | ■ | ■
20 | Architecture, Database & Integration Contracts | 2026-10-05 08:00 | 2026-10-16 17:00 |  |  |  |  | ■ | ■
21 | MF1 Detailed Design - Planning & Pre-flight Validation | 2026-10-07 08:00 | 2026-10-15 17:00 |  |  |  |  | ■ | ■
22 | MF2 Detailed Design - Monitoring & Incident Management | 2026-10-12 08:00 | 2026-10-21 17:00 | [5 empty] | ■ | ■
23 | MF3 Detailed Design - Post-Flight & Mission History | 2026-10-12 08:00 | 2026-10-21 17:00 | [5 empty] | ■ | ■
24 | MF4 Detailed Design - AI API Risk Assessment | 2026-10-12 08:00 | 2026-10-21 17:00 | [5 empty] | ■ | ■
25 | Iteration 1 - MF1 + Shared FE-01 / Software Package 1 | 2026-10-19 08:00 | 2026-10-23 17:00 | [6 empty] | ■
26 | Implement FE-01 UAV/Operator Management & Access | 2026-10-19 08:00 | 2026-10-22 17:00 | [6 empty] | ■
27 | Implement Mission Planning, Waypoints & Validation | 2026-10-19 08:00 | 2026-10-22 17:00 | [6 empty] | ■
28 | Implement Mission Approval Workflow | 2026-10-20 08:00 | 2026-10-22 17:00 | [6 empty] | ■
29 | Test MF1 / Shared Functions and Assemble Package 1 | 2026-10-21 08:00 | 2026-10-23 17:00 | [6 empty] | ■
30 | Finalize Review 2 SRS, SDD, Test Plan & Slides | 2026-10-19 08:00 | 2026-10-23 17:00 | [6 empty] | ■
31 | Submit Review 2 Dossier + Software Package 1 | 2026-10-23 17:00 | 2026-10-23 17:00 | [6 empty] | ◆
32 | Review 2 - SRS, Design & Mandatory Features (provisional W8) | 2026-10-30 17:00 | 2026-10-30 17:00 | [7 empty] | ◆
33 | Resolve Review 2 Feedback / Baseline Mandatory Features | 2026-11-02 08:00 | 2026-11-06 17:00 | [8 empty] | ■
34 | Stage 3 - Development & Testing | 2026-11-09 08:00 | 2026-12-04 17:00 | [9 empty] | ■ | ■ | ■ | ■
35 | Iteration 2 - MF2 / Software Package 2 | 2026-11-09 08:00 | 2026-11-20 17:00 | [9 empty] | ■ | ■
36 | Implement MAVLink Gateway & Telemetry Persistence | 2026-11-09 08:00 | 2026-11-12 17:00 | [9 empty] | ■
37 | Implement Real-Time Monitoring Dashboard | 2026-11-10 08:00 | 2026-11-13 17:00 | [9 empty] | ■
38 | Implement Incident Detection, Alerts & Management | 2026-11-16 08:00 | 2026-11-19 17:00 | [10 empty] | ■
39 | Test Complete MF2 / Update Reports 3-5 / Package 2 | 2026-11-17 08:00 | 2026-11-20 17:00 | [10 empty] | ■
40 | Submit Software Package 2 + Updated Reports 3-5 | 2026-11-20 17:00 | 2026-11-20 17:00 | [10 empty] | ◆
41 | Iteration 3 - MF3 + MF4 / Full Product | 2026-11-23 08:00 | 2026-12-04 17:00 | [11 empty] | ■ | ■
42 | Implement MF3 Post-Flight History, Reports & Analytics | 2026-11-23 08:00 | 2026-11-26 17:00 | [11 empty] | ■
43 | Implement MF4 External AI API Risk Assessment | 2026-11-23 08:00 | 2026-11-26 17:00 | [11 empty] | ■
44 | Integrate MF3/MF4 and Regress All Four Flows | 2026-11-25 08:00 | 2026-11-27 17:00 | [11 empty] | ■
45 | Feature-Complete Internal Build | 2026-11-27 17:00 | 2026-11-27 17:00 | [11 empty] | ◆
46 | System Testing / Defect Closure / Complete Report 5 | 2026-11-30 08:00 | 2026-12-03 17:00 | [12 empty] | ■
47 | Performance, Telemetry & Geospatial Validation | 2026-11-30 08:00 | 2026-12-02 17:00 | [12 empty] | ■
48 | AI API Functional, Context & Failure-Handling Validation | 2026-11-30 08:00 | 2026-12-02 17:00 | [12 empty] | ■
49 | Draft Report 6 - Package, Installation & User Guides | 2026-11-23 08:00 | 2026-12-03 17:00 | [11 empty] | ■ | ■
50 | Prepare Full Package, Reports 1-6 & Council 1.1 Demo | 2026-12-01 08:00 | 2026-12-04 17:00 | [12 empty] | ■
51 | Submit Council 1.1 Dossier | 2026-12-04 17:00 | 2026-12-04 17:00 | [12 empty] | ◆
52 | Stage 4 - Council 1.1 / Council 1.2 | 2026-12-07 08:00 | 2026-12-18 17:00 | [13 empty] | ■ | ■
53 | Council 1.1 Rehearsal & Document Consistency Check | 2026-12-07 08:00 | 2026-12-10 17:00 | [13 empty] | ■
54 | Council 1.1 - Defense Eligibility (provisional W14) | 2026-12-11 17:00 | 2026-12-11 17:00 | [13 empty] | ◆
55 | Prepare Report 7, Defense Slides & Final Package Draft | 2026-12-07 08:00 | 2026-12-10 17:00 | [13 empty] | ■
56 | Resolve Council 1.1 Feedback / Finalize Defense Package | 2026-12-14 08:00 | 2026-12-15 17:00 | [14 empty] | ■
57 | Submit Council 1.2 Dossier (provisional Tuesday W15) | 2026-12-15 17:00 | 2026-12-15 17:00 | [14 empty] | ◆
58 | Defense Rehearsal / Final Environment Check | 2026-12-16 08:00 | 2026-12-17 17:00 | [14 empty] | ■
59 | Council 1.2 - Official Defense (provisional W15) | 2026-12-18 17:00 | 2026-12-18 17:00 | [14 empty] | ◆
60 | Weekly Supervisor Meetings, Tracking & Weekly Reports | 2026-09-07 08:00 | 2026-12-18 17:00 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■

## Responsibility Matrix
Responsibility | ThongLQ | NghiaHQ | KhanhGNG | DucDDA | Supervisors
Project Planning & Tracking | S | D | S | S | R
Report 1 / PMP / Final Report coordination | D | S | S | S | R
Requirements & SRS | S | D | S | S | R
Architecture & Backend Integration | S | D | S | S | R
MF1 - Mission Planning & Pre-flight Validation | S | D | S | S | I
MF2 - Real-Time Monitoring & Incident Management | S | S | D | S | I
MF3 - Post-Flight Analysis & Mission History | S | S | S | D | I
MF4 - AI-Assisted Mission Risk Assessment | D | S | S | S | I
Web/Map UI | D | S | S | S | I
Mobile / Dashboard / DevOps | D | S | D | S | I
Test Planning & System Testing | S | D | S | D | I
Deployment / Demo / User Guide | D | S | S | S | R
D = Do/Owner; R = Review; S = Support; I = Informed. One primary owner per main flow; contributors support delivery.

## Plan Notes
Item | Working plan / source rule
Authority | SWP490_Lo-trinh-Capstone_v1.0.pdf, issued 09/2026, pp. 2-5: semester weeks, common submission deadlines and council stages. SE CAPSTONE PROJECT REVIEW GUIDELINE.pdf: review content, slides, minutes and feedback procedure.
Dates are provisional | Semester W1 is assumed to start Mon 07 Sep 2026 because that was the original workbook start. The PDFs do not confirm this date. Actual semester calendar, holidays, review times and room assignments must be checked against the university announcement. Recalculate dates and dependencies when confirmed.
Review windows | Review 1: W4-W5 (placeholder Fri W4, 02 Oct). Review 2: W8-W9 (placeholder Fri W8, 30 Oct). These are internal planning placeholders, not appointments issued by the university.
Common deadlines | End W3: Review 1 dossier. End W6: registration/scope freeze. End W7: Review 2 dossier and Package 1, including Iteration 1 code. End W11: Package 2 and Reports 3-5 updates. End W13: Council 1.1 dossier, full product, complete Report 5 and draft Report 6.
Councils | Council 1.1: W14 eligibility (placeholder Fri 11 Dec). Council 1.2: W15 official defense if eligible (placeholder Fri 18 Dec). Submit defense dossier at least 2 working days before actual defense; provisional submission Tue 15 Dec leaves two full working days.
Lead times | The review guideline mentions 24 hours; the September 2026 roadmap requires at least 2 working days and common earlier week-end deadlines. This plan applies the earlier applicable deadline. If an actual appointment makes the common Friday deadline too late, bring submission forward.
Review procedure | Prepare registration, slides and stage documents. Record, agree and circulate review minutes before the session ends. Track supplementary feedback for 48 calendar hours and retain minutes, correspondence and evidence; incorporate feedback at the next gate. Schedule entries do not send any communications.
Four main flows / owners | Team-confirmed allocation (16 September 2026): MF1 NghiaHQ; MF2 KhanhGNG; MF3 DucDDA; MF4 ThongLQ. Each owner coordinates requirements, design, implementation and testing for the assigned flow; other members provide support as needed.
Iterations | Iteration 1 ends W7: MF1 plus shared management / Package 1. Iteration 2 W10-W11: MF2 / Package 2. Iteration 3 W12-W13: MF3 and MF4 in parallel, integration and system tests. Four main flows do not require four iterations.
Capacity / estimates | Durations are elapsed Monday-Friday working windows, not person-days or 100% resource bookings. The 184 man-day feature envelope in Report 2 remains provisional. W7 is intensive; reuse prototypes, allocate shared work and re-estimate weekly against actual student availability.
AI scope | Configured external OpenAI or Gemini API; context preparation, response/advisory display and failure handling. Mocked tests and controlled live API smoke tests. No model training or autonomous mission approval/flight control.
Dependencies | IDs have been regenerated for the revised WBS. Bare ID = finish-to-start; SS = start-to-start; lags use working days. A zero-duration submission can occur when predecessor work finishes. Parallel testing uses SS; package gates also require implementation tasks completed.
Gantt maintenance | Static synchronized Gantt, no scheduling formulas. Bars show work windows and diamonds show milestones. Update dates, dependencies and Gantt together. Weekly tracking is a recurring 15-week window, not 75 person-days.
Weekly governance | Meet GVHD weekly; maintain Project Schedule, Project Tracking (WBS, Issues, Defects, Q&A) and Project Weekly Report. All members participate; track action owners, actual effort and capacity.
Conditional Council 2 | Only if the group fails Council 1.1 or 1.2: revise product/documents, prepare a feedback-response matrix and attend Council 2 about 4 weeks after W15 (~W19, next semester). Date TBA; dossier due at least 2 working days before session. This conditional recovery is not a mandatory extension of the 15-week baseline.
Language and revision | Reports 1-7 and council presentation use English. Revision 16 Sep 2026: team-confirmed ownership and existing cross-cutting tasks synchronized; council calendar unchanged. Original files archived in docs/archive/2026-09-16-before-team-allocation.