Capstone Project Report

Report 2 – Project Management Plan

– Ho Chi Minh, September 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 09/09/26 | A | ThongLQ | Created Project Management Plan based on Report 1 and SEP490 execution schedule. |
| 09/09/26 | A | NghiaHQ | Added scope estimation, quality objectives and project risks. |
| 09/09/26 | A | KhanhGNG | Added process, deliverables and quality/testing activities. |
| 09/09/26 | A | DucDDA | Added training, communication, configuration management and infrastructure plan. |
| 12/09/26 | M | Project team | Revised working plan: four main flows, external AI API scope, flow ownership, testing and risks; aligned dates with Project Schedule and standardized tables. |
| 12/09/26 | M | Project team | Aligned with supplied Sep 2026 council roadmap: common dossier deadlines, W6 scope freeze, W7 Package 1, W8-W9 Review 2, W14 eligibility and W15 defense; recurring tracking, submission lead times and conditional Council 2. Dates remain provisional. |
| 16/09/26 | M | Project team | Aligned flow ownership and existing cross-cutting assignments with the team decision; updated existing Web/database/version-control entries to Next.js, Supabase PostgreSQL and GitHub. No additional setup or Auth feature added. |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

DroneOps Intelligence retains the ten Major Features in Report 1, organized into four main flows. MF1: Mission Planning & Pre-flight Validation (FE-02/03/04); MF2: Real-Time Monitoring & Incident Management (FE-05/06/07 and incident functions of FE-08/10); MF3: Post-Flight Analysis & Mission History (FE-08/10); MF4: AI-Assisted Mission Risk Assessment (FE-09/10). FE-01 supports all flows. Complexity reflects integration, business rules and real-time processing. Effort remains an initial planning estimate to be refined after the SRS/design baseline.

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | FE-01 UAV & Operator Management | Medium | 12 |
| 2 | FE-02 Mission Planning & Management | Complex | 20 |
| 3 | FE-03 Mission Approval Workflow | Medium | 12 |
| 4 | FE-04 Geofence & Flight Path Validation | Complex | 24 |
| 5 | FE-05 MAVLink Telemetry Integration | Complex | 24 |
| 6 | FE-06 Real-Time Mission Monitoring | Complex | 20 |
| 7 | #### FE-07: Operational Alert and Incident Detection | Complex | 18 |
| 8 | FE-08 Incident Management & Post-Flight Analysis | Medium | 14 |
| 9 | FE-09 AI-Assisted Mission Decision Support | Medium | 24 |
| 10 | FE-10 Mission & Operational Dashboard | Medium | 16 |
| Total Estimated Effort (man-days) |  |  | 184 |

### 1.2 Project Objectives

Deliver a traceable UAV mission-operations platform for planning, pre-flight validation, real-time monitoring, incident management, post-flight review and AI-assisted risk assessment. AI uses a configured external OpenAI or Gemini API; the team implements context preparation, API integration, result display and error handling. Operators and Operations Managers review the advice; approval and operational decisions remain with authorized users. No model training or autonomous flight control is planned.

Quality objectives:

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Peer/Document Review | 100% of baseline documents reviewed | ≤ 8 major defects | ≤ 20% | Track review findings and close before baseline |
| 2 | Unit Test | ≥ 80% coverage for core backend/service logic | ≤ 15 open defects | ≤ 30% | Critical modules require unit tests |
| 3 | Integration Test | 100% critical service integrations exercised | ≤ 10 open defects | ≤ 25% | MAVLink, MQTT/WebSocket, DB, AI and map integration |
| 4 | System Test | 100% of 4 main flows + critical exceptions | 0 Critical; ≤ 5 Major open | ≤ 20% | Complete system tests by end W13; no Critical defect at council-ready release |
| 5 | Acceptance/Demo Test | 100% planned end-to-end main flows demoable | 0 Critical/Major blocking | ≤ 5% | Council 1.1 readiness W14 and official defense W15; full package submitted end W13 |

• Milestone timeliness: ≥ 90% of planned milestones completed within the target week.• Critical-flow readiness: 100% of the four main flows demonstrable by system-test/council readiness.• Release quality: 0 open Critical defects and no Major defect that blocks an end-to-end main flow.• Traceability: all baseline FRs mapped to design, implementation, test evidence and demo where applicable.

The initial 184 feature man-days are retained as a provisional planning envelope: requirements/analysis 15%, architecture/design 15%, implementation/integration 40%, testing/quality 20%, and management/documentation/deployment 10%. FE-09 covers API integration, mission context, UI, failure handling and functional validation. These are effort estimates, not elapsed task durations or full-time allocations; the four-member team reviews capacity weekly and refines estimates after the SRS baseline.

### 1.3 Project Risks

Risks are reviewed weekly. High-impact risks are escalated to the team leader and supervisors, with mitigation actions assigned an owner and due date.

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | MAVLink/simulator integration instability or inconsistent telemetry | High | Medium | Prototype early; use simulator test scenarios; isolate integration gateway; log raw telemetry. |
| 2 | Geospatial validation produces false positives/negatives | High | Medium | Define spatial rules and test datasets; unit-test waypoint/segment/polygon/altitude cases. |
| 3 | External AI API unavailable, rate-limited or over budget | High | Medium | ThongLQ owns mitigation: prototype early; configure request limits/timeouts, monitor usage, protect server-side API keys and show clear failure/retry states. Core mission functions remain available. |
| 4 | AI response is unsupported, incomplete or inconsistent with mission data | High | Medium | ThongLQ owns mitigation: send relevant available data, identify missing context, validate response structure, show source mission data and require user review. Test prepared scenarios; AI does not approve missions. |
| 5 | Scope overload across Web, Mobile, telemetry, AI and analytics | High | Medium | Prioritize four main flows; freeze registration scope at end W6; Review 2 confirms required features within that scope; defer non-critical enhancements. |
| 6 | Team member unavailable / workload imbalance | Medium | Medium | Cross-review modules; maintain shared documentation; weekly rebalance via task tracker. |
| 7 | Integration defects discovered late | High | Medium | Prototype early; incremental testing from W7 Package 1; CI checks and regression through Packages 2 and 3; complete system-test dossier by end W13. |
| 8 | Deployment/network service failure before review/council | High | Low | Maintain reproducible deployment, local fallback/demo environment and pre-event readiness checklist. |
| 9 | W7 Package 1 deadline exceeds available student capacity | High | Medium | NghiaHQ coordinates MF1; reuse W2-W3 prototypes, complete preparatory design in W5-W6 and share FE-01 work. Review member availability weekly; escalate delivery risk early without moving mandatory submission deadlines. |

## 2. Management Approach

The team uses incremental development around four main flows, weekly supervisor meetings, tracking and documented reviews. The controlling timeline is SWP490_Lo-trinh-Capstone_v1.0 (09/2026): Review 1 in W4-W5, Review 2 in W8-W9, Council 1.1 eligibility in W14 and Council 1.2 defense in W15. The SE Capstone Project Review Guideline supplies review content and minutes procedures; its Final Product review content is prepared for the council stage rather than scheduled as an additional W13 review.

### 2.1 Project Process

Four main flows are delivered through three iterations. Iteration 1 completes MF1 Mission Planning & Pre-flight Validation plus shared FE-01 by end W7 as Software Package 1. Iteration 2 in W10-W11 implements MF2 Real-Time Monitoring & Incident Management for Software Package 2. Iteration 3 in W12-W13 delivers MF3 Post-Flight Analysis & Mission History and MF4 AI-Assisted Mission Risk Assessment in parallel, then integrates and system-tests all four flows. Feasibility prototypes in W2-W3 and preparatory design in W5-W6 support the W7 code deadline; W8-W9 accommodates Review 2 and mandatory-feature feedback. Iteration count does not change the four-flow scope.

### 2.2 Quality Management

Quality is managed through prevention, peer review, automated/unit testing, integration testing, system testing and traceability. Definition of Done requires updated documentation, reviewed code, passing tests and demo evidence for each completed main flow.

• Defect Prevention: coding conventions, API contracts, architecture/design reviews, reusable validation rules, CI checks and early technical prototypes.

• Reviewing: peer review for requirements/design/code; supervisor review at weekly checkpoints; review feedback is logged and closed with evidence.

• Unit Testing: core backend services, geospatial validation, incident rules, AI context preparation, response validation and error handling using mocked provider responses.

• Integration Testing: simulator/UAV to gateway, telemetry persistence and real-time clients; validation to approval; incident/history/report integration; configured OpenAI or Gemini API success, timeout, rate-limit and malformed-response scenarios. Live API smoke tests complement repeatable mocked tests.

• System Testing: end-to-end execution of the four main flows plus critical exception scenarios, latency/reliability checks and regression tests.

### 2.3 Training Plan

Training is performed as targeted self-study and technical prototyping before the corresponding implementation increment. Knowledge is shared through short internal walkthroughs and code reviews.

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| MAVLink + UAV simulator integration | ThongLQ, NghiaHQ, KhanhGNG, DucDDA | W2–W3, 2–3 days | Waived if member can ingest and parse simulator telemetry end-to-end |
| Geospatial algorithms / geofence validation | NghiaHQ, KhanhGNG, DucDDA | W2–W5, 2 days | Waived after passing route/polygon/altitude prototype tests |
| External AI API integration and response handling | All members; ThongLQ leads | W2-W3 prototype; W6 design, 2-3 training days | Waived after demonstrating mission-context request, valid response display, timeout/rate-limit handling and secure server-side API configuration |
| ASP.NET Core / Next.js / EF Core project conventions | All members | W2-W6, ongoing self-study | Waived after code review confirms team conventions |
| Flutter/Riverpod & real-time client updates | ThongLQ, NghiaHQ, KhanhGNG, DucDDA | W5-W7, 2 days | Waived after mobile/dashboard prototype |
| Testing, Git workflow & CI/CD | All members | W2-W6, 1-2 days | Mandatory baseline; practical check through PR + test pipeline |

## 3. Project Deliverables

The plan follows the supplied September 2026 roadmap (pp. 2-5), using semester weeks as authoritative. Calendar dates assume W1 begins 07 September 2026; this assumption and all individual appointments require confirmation from university announcements. Current placeholders are Review 1 on 02 October (W4), Review 2 on 30 October (W8), Council 1.1 on 11 December (W14), and Council 1.2 on 18 December (W15). Common dossier deadlines are end W3, W7 and W13; defense documents are due at least two working days before the actual session. Where the guideline states 24 hours, this plan applies the stricter roadmap lead time and earlier common deadline. Adjust submission dates earlier if required by the actual appointment.

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 - Project Introduction | End W1 | Scope, ten features, actors, context and four main flows |
| 2 | Report 2 + Project Schedule | End W2 | Management plan, WBS, risks, responsibilities and schedule |
| 3 | Review 1 dossier | End W3 | Registration; Reports 1-2; Report 3 overview (Product Overview, User Requirements, System Functional Overview); Project Tracking and review slides |
| 4 | Review 1 minutes / feedback | W4-W5 | Review appointment TBA; agree/circulate minutes before session end; 48-calendar-hour feedback window |
| 5 | Confirmed registration / scope baseline | End W6 | Update if required by Review 1; supervisor confirmation; scope frozen after W6 |
| 6 | Review 2 dossier + Software Package 1 | End W7 | Full Report 3 SRS; Report 4 SDD; Report 5 Test Plan; Iteration 1 source/database scripts; updated Reports 1-2, Tracking and slides |
| 7 | Review 2 minutes / mandatory feature list | W8-W9 | Requirements and design feedback; required features remain within the W6 registration scope |
| 8 | Software Package 2 + Reports 3-5 updates | End W11 | Complete MF2 increment, source/database scripts, updated design and test records |
| 9 | Council 1.1 dossier / Full Software Package | End W13 | Reports 1-6; complete Report 5 test cases/results/defect list; draft Report 6; registration, review minutes, Tracking and demo |
| 10 | Council 1.1 eligibility decision | W14 | Three-member council checks product against registration, SRS, design and required feature list |
| 11 | Council 1.2 dossier / Report 7 / final package | At least 2 working days before defense | Report 7, defense slides, source/database scripts, testing documents and Tracking. Provisional submission Tue 15 Dec for Fri 18 Dec defense |
| 12 | Council 1.2 - official defense | W15 | Conditional on passing Council 1.1; all members present/demo/respond |
| 13 | Weekly Report / Project Tracking | Every week | GVHD meeting; WBS, Issues, Defects, Q&A, risk/capacity and feedback tracking |
| 14 | Council 2 recovery package (conditional) | About W19; date TBA | Only after failure at Council 1.1 or 1.2; next semester, about four weeks after W15; revised product/docs and feedback-response matrix; submit at least 2 working days before session |

## 3.1 High-Level 15-Week Schedule

| Week | Phase / Gate | Key Activities | Primary Output |
| --- | --- | --- | --- |
| W1 | Initiation | Registration, supervisor coordination, scope and context | Report 1 by end W1 |
| W2 | Planning / Feasibility | PMP, Schedule, risks and technical prototypes | Report 2 + Schedule by end W2 |
| W3 | Requirements Overview | Report 3 overview, Tracking and Review 1 slides/dossier | Review 1 dossier submitted by end W3 |
| W4 | Review 1 window | Provisional review Fri W4; official window W4-W5; record minutes | Feasibility/scope feedback |
| W5 | Scope refinement / preparation | Review 1 if assigned W5; feedback; SRS, architecture and MF1 design | Updated requirements/design drafts |
| W6 | Scope freeze | Resolve scope feedback; supervisor-confirmed registration; design preparation | Registration frozen by end W6 |
| W7 | Iteration 1 / Review 2 submission | Complete MF1/shared FE-01; finalize SRS, SDD and Test Plan | Package 1 + Review 2 dossier by end W7 |
| W8 | Review 2 window | Provisional review Fri W8; official window W8-W9 | Minutes, design feedback and required features |
| W9 | Review 2 / feedback closure | Review if assigned W9; baseline feature list and revise backlog | Updated SRS/SDD/Test Plan within frozen scope |
| W10 | Iteration 2 | MF2 gateway, persistence and monitoring | Integrated monitoring build |
| W11 | Iteration 2 completion | MF2 incidents/alerts; tests and Reports 3-5 updates | Software Package 2 by end W11 |
| W12 | Iteration 3 | MF3 post-flight and MF4 AI API in parallel; integrate; draft user guides | Internal feature-complete build |
| W13 | System tests / Council submission | System tests, defects, complete Report 5 and draft Report 6; full package | Council 1.1 dossier by end W13 |
| W14 | Council 1.1 - Eligibility | Three-member council; product/document review; prepare defense draft | Eligibility decision and feedback |
| W15 | Council 1.2 - Defense | Close feedback; submit dossier at least 2 working days before defense; rehearse | Report 7, final product and official defense if eligible |

## 4. Responsibility Assignments

Responsibility codes: D = Do/Owner; R = Review; S = Support; I = Informed. Team-confirmed allocation (16 September 2026): MF1 NghiaHQ; MF2 KhanhGNG; MF3 DucDDA; MF4 ThongLQ. Each owner coordinates requirements, design, implementation and testing for the assigned flow; other members provide support as needed. Existing cross-cutting responsibilities follow the agreed allocation: ThongLQ coordinates Web frontend, GitHub, database/deployment work; NghiaHQ coordinates backend integration and project tracking. Resource Names identify contributors rather than full-time bookings.

D = Do/Owner; R = Review; S = Support; I = Informed; blank = Omitted.

| Responsibility | ThongLQ | NghiaHQ | KhanhGNG | DucDDA | Supervisors |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | S | D | S | S | R |
| Report 1 / PMP / Final Report coordination | D | S | S | S | R |
| Requirements & SRS | S | D | S | S | R |
| Architecture & Backend Integration | S | D | S | S | R |
| MF1 - Mission Planning & Pre-flight Validation | S | D | S | S | I |
| MF2 - Real-Time Monitoring & Incident Management | S | S | D | S | I |
| MF3 - Post-Flight Analysis & Mission History | S | S | S | D | I |
| MF4 - AI-Assisted Mission Risk Assessment | D | S | S | S | I |
| Web/Map UI | D | S | S | S | I |
| Mobile / Dashboard / DevOps | D | S | D | S | I |
| Test Planning & System Testing | S | D | S | D | I |
| Deployment / Demo / User Guide | D | S | S | S | R |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Weekly GVHD meeting / Weekly Report | All members + supervisors | Review progress/capacity; update WBS, Issues, Defects and Q&A | Weekly W1-W15 | Meeting, Project Tracking and Project Weekly Report |
| Daily team coordination | All members | Task progress, blockers and shared implementation | Working days | Team chat + task board |
| Pull Request / Code Review | Developers + reviewer | Source quality and reproducible evidence | Per PR | Repository PR, review comments and CI |
| Review/Council dossier submission | Team to supervisors/reviewers/council | Send registration, slides and required documents | End W3/W7/W13; defense >=2 working days before | Use the announced channel; apply earlier deadline if actual appointment requires it |
| Review meeting / minutes | All members, GVHD and reviewers | Present; agree checklist/findings; record and circulate minutes | W4-W5 and W8-W9; minutes before session end | Prescribed minutes and email procedure; retain evidence |
| Supplementary review feedback | Team, GVHD and reviewers | Resolve or record additions to agreed minutes | Within 48 calendar hours after review | Reply to review minutes thread; archive correspondence |
| Council sessions / feedback | All members + council | W14 eligibility; W15 defense if eligible | W14 / W15, appointments TBA | Demo, presentation, minutes and feedback-response tracking |
| Risk/Issue Escalation | Owner -> leader -> supervisors | Resolve high-impact delivery issues | As needed; within 24h for high impact | Issue tracker + direct communication |

## 6. Configuration Management

### 6.1 Document Management

Maintain English Reports 1-7 using course templates, Project Schedule, Project Tracking and Weekly Reports in the shared document workspace with version labels and archived baselines. Freeze the supervisor-confirmed registration at end W6; Review 2 records mandatory features within that scope. Retain review/council minutes, feedback correspondence and evidence; update the Record of Changes and traceability after each gate. Submit common dossiers at end W3, W7 and W13 and the defense dossier at least two working days before the actual appointment. Only groups failing Council 1.1 or 1.2 prepare the conditional Council 2 package with a feedback-response matrix about four weeks after W15.

### 6.2 Source Code Management

Source code is managed in Git. Work is performed on feature/fix branches and merged through pull requests after review. The main/develop branch policy, commit naming, issue references and release tags are agreed by the team. Secrets are excluded from source control and provided through environment configuration. Review/council builds are tagged so they can be reproduced.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Web frontend: Next.js; backend: C# / ASP.NET Core; existing mobile scope: Flutter/Dart (Riverpod); MAVLink; MQTT/WebSocket; configured OpenAI or Gemini API called from the backend. |
| Database / Data Access | Supabase PostgreSQL; Entity Framework Core for backend data access; mission, telemetry, incident and report persistence. ThongLQ coordinates database/deployment work; NghiaHQ coordinates backend integration. |
| IDEs/Editors | Visual Studio / Visual Studio Code; Android Studio as needed |
| Diagramming | Draw.io / diagrams.net, PlantUML or equivalent |
| Documentation | Microsoft Word/Excel, Google Drive/Docs/Sheets |
| Version Control | GitHub repository with feature branches, pull requests and tagged baselines; ThongLQ coordinates repository work. |
| Deployment / CI | Deployment and CI build/test pipeline coordinated by ThongLQ; environment configuration keeps credentials outside source control. |
| Testing / Simulation | MAVLink-compatible UAV simulator/autopilot environment; unit/integration/system test tools |